## Project List (hidden)
| Title | Governance | Year 1 Value | Year 5 Value | Implementation Score | Business Benefit Score
ESB Energy | PAY: Review of GSOP Report
ESB Energy | CX: Power BI report - Digital stats
ESB Energy | IMS: Smart billing report
ESB Energy | IMS: Smart Gas Reads
ESB Energy | BIL: Report to monitor the production of Final Bills resulting from COT
ESB Energy | ONB: Rebuilding Onboarding Dashboard
ESB Energy | IMS: FMR - Multiple Meterpoint
ESB Energy | IMS: FMR Electricity Report - Single Meterpoint
ESB Energy | ONB: Consumption used to set up account vs industry EAC/AQ
ESB Energy | IMS: Rebuilding ESB Energy customers - Dual Fuel customer, a Single Fuel Electric customer and Single Fuel Gas customer Dashboard
ESB Energy | IMS: Rebuilding MSN Mismatch Dashboard
ESB Energy | MRK: Renewals Weekly Analysis
ESB Energy | CX: DD Failed Collection
ESB Energy | CSR: Meter Read Reporting
ESB Energy | BIA: Smart Eligibility Process
ESB Energy | ONB: CR - Telesales Audit Reports
ESB Energy | SAL: Telesales report to specifically be able to drop down to time periods and patner or agent level - giving a ranking leaderboard
ESB Energy | REG: Request for Information
ESB Energy | IMS: Smart Read Validation Report
ESB Energy | IMS: E7 Report
ESB Energy | MRK: Marketing opt in report
ESB Energy | CX: Change Request - ESB Energy SSD comm (Refer a Friend)
ESB Energy | CX: Business Benchmarking research with Insitute of Customer Service
ESB Energy | CX: Campaign file performance review
ESB Energy | CX: Refer a Friend once monthly update - email
ESB Energy | CX: Change Request - add RaF details to daily Welcome Email campaign file
ESB Energy | BIA: Data Source: Trust Pilot
ESB Energy | BI: Customer Data in different data sources - Review
ESB Energy | BIA: Customer Data Quality issues dashboard
ESB Energy | BIA: Customer Numbers Dashboard
ESB Energy | BIA: Renewals R Code Transition
ESB Energy | BIA: Customer Value Model
ESB Energy | BIA: Power BI Servers Upgrade
ESB Energy | BIA: Review of code for BI data
Customer Solutions | Pan ESB Customer Experience Dashboard
Electric Ireland | Segmentation required for new acqusition door drop
Electric Ireland | Dashboard/Tableau Daily Summary on Call Trends
Electric Ireland | Automate CMOS Dataload
Electric Ireland | Review SAP Marketing Cloud data
Electric Ireland | EI Smart Metering Project
Electric Ireland | Payments Analysis
Electric Ireland | NI: Digital Dashboard
Electric Ireland | NI PAYG Statements
Electric Ireland | Hybris Transition
Electric Ireland | ROI: Digital Dashboard
Electric Ireland | Priority Emails Analysis
Electric Ireland | Time Switch Analysis
Electric Ireland | SME Value Model
Electric Ireland | Development of New Pricing Dashboard for Prompt Trading Team
Electric Ireland | Update of Competitor list on Prompt Trading dashboard
Electric Ireland | Front Office Auction Dashboard
Electric Ireland | PAYG Statements
Electric Ireland | PAYG Compliance & Revenue Protection Report
Electric Ireland | PAYG Analysis
Electric Ireland | Token Meter Customers
Electric Ireland | Customer Gains/Losses
Electric Ireland | PSI Leads NI
Electric Ireland | Customer Numbers
Electric Ireland | DD customers that make card payments
Electric Ireland | Residential Customer Profiling - churn modelling
Electric Ireland | Customer Service Dashboard
Electric Ireland | BOL Registered Accounts in SAP Marketing Cloud
Customer Solutions | New Product Development dashboard
Electric Ireland | Monthly FCR Report for SME Sales & Service Calls
Customer Solutions | Insight of Heat Pump Customers Consumption Pattern
Customer Solutions | Call Recording Speech to Text
Electric Ireland | Repeat Contact Bayes Net Model
Electric Ireland | NI Win back/ data required
Electric Ireland | SuperSaver 30 Day Comms Issue
Electric Ireland | Qualitative insight from CRM Queries & Complaints
Electric Ireland | SPAYG Statements to Business Objects
Electric Ireland | Creation of New Sales Report
Customer Solutions | EV Customers Energy Consumption Insights
Electric Ireland | NI RES PAYG Vat
Electric Ireland | customer report per sales channel
Electric Ireland | Customer Analysis for Loyalty Lottery
Electric Ireland | Change in SPAYG consumption over the past four weeks
Electric Ireland | Smart Metering Impact reporting
Electric Ireland | Report to identify COS Acquisitons & New Connections including Payment Method
Electric Ireland | SPC needed for Covid 19 Suspension
Electric Ireland | CollectSure Project
Electric Ireland | Switch Cancellation Reason Report
Electric Ireland | Tenure of Old & New Customers from attached raw data & their payment methods
SES | SES Online Reporting Platform
Electric Ireland | Data Quality Dashboards Improvements
Electric Ireland | Refresh SME Value Model 2020
Electric Ireland | NI PAYG Statements 2019
ESB Energy | Trustpilot - Modify, Test and deploy on DMZ
Electric Ireland | List of customer names who have received our Gas Insert in their bill in July
Electric Ireland | SMART Metering - RM106 dashboard
Electric Ireland | New Report - WR 79703- CRM Customer Pain Point Identifier
Electric Ireland | WR180- ​Analysis required as to how kWh & carbon tax kWh are being treated in BEW sales usage query
Electric Ireland | Change of Supplier (CRU Industry)
Electric Ireland | Total Consumption 2018
Electric Ireland | Monthly losses trend
Electric Ireland | Power BI unit to be added to ESBIE ROI
Electric Ireland | Monthly SME ebilling goverance report
Electric Ireland | Legacy T035 Meters in IRP with availability charge
Electric Ireland | NI Consumption for 1/4/19 - 31/3/20
Electric Ireland | Customer information
Electric Ireland | Cost and Consumption report - Government Agencies Contract
Electric Ireland | Customer data request
ESB Telecoms | Business Geo-Data

## Benefits and Realisation
What is expected to change
Current Customer Numbers | 144000 |  | How much (% / # / €) |  |  |  | Go Live Date | 2020-08-19
Estimated margin per customer | 25 |  | How often |  |  |  | End Evaluation Date | 2021-02-15
WBS |  |  | How much time is saved |  |  |  | 180 | days evaluation
Reporting / Analysis |  |  | As is status |  | To be Status |  | End Result
Success KPIs | Cost to Serve Reduction |  | Success KPIs | Cost to Serve Reduction | Success KPIs | Cost to Serve Reduction | Success KPIs | Cost to Serve Reduction
Details | understand what is driving these contacts in order to drive improvements. We feel this may improve the following : FCR Cost to Serve Reduce AHT Improve the Cutsomer Experience and positively impact CSAT & NPS scores Reduce Churn |  |  |  |  | Manual effort in call listening estimated @500 hours 5% reduction in cost to serve including improvemnts in following: - FCR - Reduce AHT - Improve the Cutsomer Experience - positively impact CSAT & NPS scores - Reduce Churn | Actual Success Value at end of evaluation period
Frequency of Impact | Once Off |  | Frequency of Impact | Once Off | Frequency of Impact | Once Off | Frequency of Impact | Once Off
Severity of Not Implementing | Medium |  | Severity of Not Implementing | Medium | Severity of Not Implementing | Medium | Severity of Not Implementing | Medium
Expected % change | -5% |  | Current Volume | 79 | To Be Volume | 75.05 | Evaluation End Point Actual % | 0%
[5 empty] | Expected Value of Increase / Decrease | -568800 | Evaluation End Point Actual Value | 0
Expected FTE saving or decrease (Hours) | 500 |  | Current FTE involved (Hours) |  | Reduction in FTE (Hours) | 500 | Actual Reduction in FTE (Hours)
[5 empty] | Expected Value of FTE Decrease | 53500 | Actual Annual Value of FTE Decrease | 0
Evaluation Timeframe | 3 - 6 Months
[5 empty] | Estimated Saving / Cost Reduction | 622300 | Actual Saving / Cost Reduction | 0
[5 empty] | Estimate Analytics Cost | 151800 | Actual Analytics Cost | 0
[5 empty] | Total Value Year 1 | 470500 | Total Value | 0
[5 empty] | Total Value (Over 5 years) | 2959700 | Total Value (Over 5 years) | 0
| FALSE | FALSE | Customer Growth | Daily
| FALSE | FALSE | Gross Margin Improvement | Weekly
| -568800 | 0 | Cost to Serve Reduction | Monthly
| FALSE | FALSE | Cost to Acquire Reduction | Quarterly
| 0 | 0 | Churn Reduction | Once Year
| FALSE | FALSE | Retention Increase | Once Off
| 0 | 0 | Process Efficiency
| 0 | 0 | Increase Productivity
| 0 | 0 | Reduce Non Value Add Activities
| 0 | 0 | Reduce FTE
| FALSE | FALSE | Increase Customer Satisfaction
| FALSE | FALSE | Increase NPS
| FALSE | FALSE | Increase Trust Pilot Score

## Hours&Costs
Estimated |  |  | Actuals
Hours CS Analytics Team | 178 |  | Hours CS Analytics Team
Estimate CS Analytics Cost | 106800 |  | Estimate CS Analytics Cost | 0
Hours Engineering Team | 50 |  | Hours Engineering Team
Estimate Engineering Cost | 30000 |  | Estimate Engineering Cost | 0
Hours BW/BO Team |  |  | Hours BW/BO Team
Estimate BW/BO Cost | 0 |  | Estimate BW/BO Cost | 0
Hours SSIS Team |  |  | Hours SSIS Team
Estimate SSIS Cost | 0 |  | Estimate SSIS Cost | 0
Hours Cloud Desk Team |  |  | Hours Cloud Desk Team
Estimate Cloud DeskO Cost | 0 |  | Estimate Cloud DeskO Cost | 0
Hours Digital Team |  |  | Hours Digital Team
Estimate Digital Cost | 0 |  | Estimate Digital Cost | 0
Hours Framework |  |  | Hours Framework
Estimate Digital Cost | 0 |  | Estimate Digital Cost | 0
Hardware | 0 |  | Hardware | 0
License Costs | 0 |  | License Costs | 0
Additional Support Costs | 15000 | Cost per min, for Cognitive Services | Additional Support Costs | 0
Contingency Costs | 0 |  | Unidentified Costs | 0
Expected Fines | 0 |  | Received Fines | 0
Total Cost | 151800 |  | Total Cost | 0
Total Hours | 228 |  | Total Hours | 0

## Timelines
Week | W1 (Sprint 7) | W2 | W3 | W4 | W5 | W6 | Week | W7 (Sprint 8) | W8 | W9 | W10 | W11 | W12 | Week | W13 | W14 | W15 | W16 | W17 | W18
| 2020-10-12 | 2020-10-19 | 2020-10-26 | 2020-11-02 | 2020-11-09 | 2020-11-16 |  | 2020-11-23 | 2020-11-30 | 2020-12-07 | 2020-12-14 | 2020-12-21 | 2020-12-28 |  | 2021-01-04 | 2021-01-11 | 2021-01-18 | 2021-01-25 | 2021-02-01 | 2021-02-08
Stakeholder Engagement | Kick Off | Requirements |  | 1st Phase Dev | 1st Phase Dev | 2nd Phase Dev | Stakeholder Engagement | 2nd Phase Dev | 2nd Phase Dev | 3rd Phase Dev | 3rd Phase Dev |  |  | Stakeholder Engagement
Approach | [6 empty] | Approach | [6 empty] | Approach
Activities | Task 1 : Requirment Analysis for Bill Shock Investigation. Task 2: Indentify the development activities for Bill Shock Investigation Project. Task 3 : Timeline for each development task should be estimated. | Task 1 : Azure Speech API Billing Cost Estimation. Task 2 : VoicetoText Architecture Design. Task 3 : Analyze the Voice Calls From Business Team. | Task 1 : Create Request with Azure Cloud Team to create the Cloud Services in Test Environement . Task 2 : Develop API to read & write the file Azure Blob Storage. | Task 1 : Develop Code to ingest the Voice Files into Azure Blob Storage. Task 2 : Develop Code & Test functionality of Azure Blob trigger. Task 3 : Develop Code & Test functionality of Azure Time trigger. | Task 1 : Develop Code to ingest the Voice Files into Azure Blob Storage. Task 2 : Develop Code & Test functionality of Azure Blob trigger. Task 3 : Develop Code & Test functionality of Azure Time trigger. | Task 1 : Integration of Azure Speech API & Azure Blob Storage. Task 2 : Develop Code to transcribe the Voice calls to Text using Azure Speech API. Task 3 : Design & Finalize the Approach to process Voice calls parallely. | Activities | Task 1 : Integration of Azure Speech API & Azure Blob Storage. Task 2 : Develop Code to transcribe the Voice calls to Text using Azure Speech API. Task 3 : Design & Finalize the Approach to process Voice calls parallely. | Task 1 : Create Request with Azure Cloud Team to create the Cloud Services in Prod Environement . Task 2 : Develop Automation Framework to execute Daily or weekly Based on the Requirment. | Task 1 : Create Request with Azure Cloud Team to create the Cloud Services in Prod Environement . Task 2 : Develop Automation Framework to execute Daily or weekly Based on the Requirment. | Task 1 : Deploy & Monitor the VoicetoText Code in Production Environement . Task 2 : Develop code to copy from Azure Blob Storage into Local Share Drive or other location based on the Business Demand. |  |  | Activities
Output/ Deliverables | Output 1 : Requirment Analysis for Bill Shock Investigation should be completed. Output 2 : All Development Task & Timeline with hours should be updated in the user story. | Output 1 : Billing Cost Estimation for Azure Speech API should be estimated. Output 2 : Cloud Service componenets & Project Architecture Design should be finalized. Output 3 : Monthly Voice Calls or Daily Call voulme & size should be analyzed. | Output 1 : Azure Cloud Services should be created in Test Environement. Output 2 : API for reading & writing the file Azure Blob Storage should be test & completed. | Output 1 : Data Ingestion for Voice Files into Azure Blob Storage should be completed. Output 2 : Azure Blob & Time trigger code should be developed and Tested. | Output 1 : Data Ingestion for Voice Files into Azure Blob Storage should be completed. Output 2 : Azure Blob & Time trigger code should be developed and Tested. | Output 1 : Integration between Azure Speech API & Azure Blob Storage should be completed. Output 2 : VoiceToText Speech API code using Azure Speech API should be completed. Output 3 : Multiple Voice Call Processing Code should be Completed. | Output/ Deliverables | Output 1 : Integration between Azure Speech API & Azure Blob Storage should be completed. Output 2 : VoiceToText Speech API code using Azure Speech API should be completed. Output 3 : Multiple Voice Call Processing Code should be Completed. | Output 1 : Azure Cloud Services For Bill shock Investigation project should be completed in Prod Environement . Output 2 : Develop Automation Framework for Azure Speech API should be completed. | Output 1 : Azure Cloud Services For Bill shock Investigation project should be completed in Prod Environement . Output 2 : Develop Automation Framework for Azure Speech API should be completed. | Output 1 : VoicetoText Code should be deployed in Production Environement . Output 2 : Transcribed Results should be delivered to the Business on daily/weekly depends on requirement. |  |  | Output/ Deliverables
Approach
Templates
Activity
Examples
Delivery
Output
Examples
Formulas:
W2 = [W1 (Sprint 7)]+7
W3 = [W2]+7
W7 (Sprint 8) = [W6]+7
W8 = [W7 (Sprint 8)]+7
W9 = [W8]+7
W13 = [W12]+7
W14 = [W13]+7
W15 = [W14]+7
Backlog
Mobilise and Planning
Current State Analysis & Quick Win Identification
Future State Design & Quick Win Implementation
Business Handover
Business Rollout
Meetings with key stakeholders
Agree list of key impactful questions
Initial data exploration including availability and quality
Review some of initial impactful questions to understand opportunity for depth and breadth of analysis
Design of solution
Agree key data items
Agree rough format of Tableau dashboards
Get permanent access to all systems
Scope and success criteria
Key data requirements & review of current state
Scoping document
Time boxing
Estimation of tasks
Data preparation including full data quality checks, cleanse activities, scaling and joining.
Feature engineering
Develop links between Tableau and Database
Develop Tableau Dashboard
Cleansed dataset for analysis & log of data quality issues
Model selection assessment
Model output and visualization
Sales/Operational data features database
Sales/Operational dashboard
Data quality assessment
Communicate opportunities identified
Deep-dive and validate opportunities
Extend model / analysis as needed
Review potential business recommendations
Develop Tableau Dashboard
List of opportunities and recommendations
Documented tool
Credit Control data features database
Credit Control dashboard
Handover code including a demo run
Handover documentation to agreed point of contact
Handover database and dashboard
Walk business through two dashboards
Documented tool, data & recommendations
Handover documentation
Design and Planning
Early Stage Development
Late Stage Development
Embedding to Production
Hypercare
Backlog
Design and Planning
Early Stage Development
Late Stage Development
Embedding to Production

## Lists (hidden)
Yes | 0 - 3 Months | Severity of not implementing | Key Digital Themes | Analytics Strategy Alignment | ESB Strategy | Benefit | Daily
No | 3 - 6 Months | Low | Customer | Connecting with Data (Providing?) | Put customers’ current and future needs at the centre of all our activities | Customer Growth | Weekly
| 6 - 12 Months | Medium | Employee | Insightful Data Stories (Help them?) | Produce, connect and deliver clean, secure and affordable energy | Gross Margin Improvement | Monthly
| 12 - 24 Months | High | Operations & Asset Mgt. | Data Literacy / Culture ( Help themselves?) | Develop energy services to meet emerging market needs | Retention Increase | Quarterly
| 2 - 5 Years | Critical |  |  | Grow the business whilst maintaining ESB’s financial strength | Increase Productivity | Once Year
| > 5 Years |  |  |  | Deliver a high-performance culture that supports innovation and collaboration | Increase Customer Satisfaction | Once Off
Increase NPS
Increase Trust Pilot Score
Churn Reduction
Cost to Serve Reduction
Cost to Acquire Reduction
Reduce FTE
Reduce Non Value Add Activities
Process Efficiency
Regulatory Impact